## Sheet1
Work Breakdown Structure
Sr No | Work Item | Dependencies | Connect With | Work Allocated To | Target Date | Status
Pre-Requisite
1 | Git Repository |  |  | Darshan | 2023-06-30 | Closed
Implementation
1 | Wire Frames |  |  | Vaishnavi | 2023-06-30 | Closed
2 | Logo Design |  |  | Dipak | 2023-06-30 | Closed
3 | Angular Project Creation |  |  | Dipak | 2023-06-30 | Closed
4 | DataBase Hosted on MsSql |  |  | Darshan | 2023-07-01 | Closed
5 | Scaffolding of DataBase |  |  | Darshan | 2023-07-01 | Closed
6 | API Creation - Employee Rest API |  |  | Darshan | 2023-07-01 | Closed
7 | API Creation - Stores Rest API |  |  | Roshan | 2023-07-01 | Closed
8 | API Creation - Authors Rest API |  |  | Parth | 2023-07-01 | Closed
9 | API Creation - Titles Rest API |  |  | Dipak | 2023-07-01 | Closed
10 | API Creation -Publishers Rest API |  |  | Vaishnavi | 2023-07-01 | Closed
11 | API Creation - Jobs Rest API |  |  | Suyog | 2023-07-01 | Closed
12 | API Creation - Sales Rest API |  |  | Prashant | 2023-07-01 | Closed
13 | API Creation - Login Rest API |  |  | Darshan | 2023-07-02 | Closed
14 | API Creation - Sign up Rest API |  |  | Darshan | 2023-07-02 | Closed
15 | UI Creation - HomePage (Dashboard) UI |  |  | Parth | 2023-07-03 | Closed
16 | UI Creation - Login Page |  |  | Dipak | 2023-07-04 | Closed
17 | UI Creation - Sign Up Page |  |  | Dipak | 2023-07-05 | Closed
18 | Angular UI Integration with API - Login Page |  |  | Parth | 2023-07-05 | Closed
19 | Angular UI Integration with API - Sign Up Page |  |  | Dipak | 2023-07-05 | Closed
20 | Angular UI Intergration with API - Publisher on Dashboard |  |  | Parth | 2023-07-05 | Closed
21 | Angular UI Intergration with API - Author on Dashboard |  |  | Parth | 2023-07-05 | Closed
22 | Angular UI Intergration with API - All Employees on Dashboard |  |  | Darshan | 2023-07-06 | Closed
23 | Angular UI Intergration with API - All Authors on Dashboard |  |  | Parth | 2023-07-06 | Closed
24 | Angular UI Intergration with API - All Books on Dashboard |  |  | Parth | 2023-07-06 | Closed
25 | Angular UI Integration with API - All Stores on Dashboard |  |  | Parth | 2023-07-06 | Closed
26 | UI Creation - Profile Page for Author UI |  |  | Parth | 2023-07-06 | Closed
27 | UI Creation - Profile Page for Publisher UI |  |  | Dipak | 2023-07-06 | Closed
28 | UI Creation - Title Publish Request UI |  |  | Dipak | 2023-07-06 | Closed
29 | Angular UI Integration with API - Login Page |  |  | Dipak | 2023-07-07 | WIP
30 | Angular UI Integration with API - SignUp Page |  |  | Dipak | 2023-07-07 | WIP
31 | Angular UI Intergration with API - Own Book Title Update by Author |  |  | Parth | 2023-07-06 | WIP
32 | Angular UI Intergration with API - Author Title Publish Request |  |  | Darshan | 2023-07-07 | WIP
33 | Angular UI Intergration with API - Publish request accept from Publisher |  |  | Darshan | 2023-07-07 | WIP
Quality Assuarance
1 | API Testing - Login Page |  |  | Roshan | 2023-07-03 | Closed
2 | API Testing - Sign Up Page |  |  | Prashant | 2023-07-03 | Closed
3 | API Testing - Dashboard Page |  |  | Vedant | 2023-07-03 | Closed
4 | API Testing - Employees |  |  | Vedant | 2023-07-03 | Closed
5 | API Testing - Jobs |  |  | Vedant | 2023-07-03 | Closed
6 | API Testing - Authors |  |  | Vedant | 2023-07-03 | Closed
7 | API Testing - Publishers |  |  | Suyog | 2023-07-04 | Closed
8 | API Testing - Stores |  |  | Vaishnavi | 2023-07-04 | Closed
9 | API Testing - Titles |  |  | Parth | 2023-07-04 | Closed
10 | Angular Integration Testing - Login Page |  |  | Dipak | 2023-07-06 | Closed
11 | Angular Integration Testing - Sign up Page |  |  | Roshan | 2023-07-06 | Closed
12 | Angular Integration Testing - Dashboard |  |  | Prashant | 2023-07-06 | Closed
13 | Angular Integration Testing - Employees |  |  | Vaishnavi | 2023-07-06 | Closed
14 | Angular Integration Testing - Stores |  |  | Vaishnavi | 2023-07-06 | Closed
15 | Angular Integration Testing - Own Titles by Author |  |  | Prashant | 2023-07-07 | WIP
16 | Angular Integration Testing - Authors |  |  | Suyog | 2023-07-07 | WIP
17 | Angular Integration Testing - Publishers |  |  | Vedant | 2023-07-07 | WIP
Deployment
1 | Deployment Strategy |  |  | All Members | 2023-07-06 | WIP
2 | Setup - for deployment - Angular App |  |  | Roshan | 2023-07-07 | WIP
3 | Setup - for deployment - Web API |  |  | Roshan | 2023-07-07 | WIP
4 | Setup - Dependendat Resources |  |  | Vaishnavi | 2023-07-07 | WIP
5 | Setup - Storage Account |  |  | Vedant | 2023-07-07 | WIP
6 | Setup - Blob Storage |  |  | Vedant | 2023-07-07 | WIP
7 | Setup - Logic App |  |  | Vaishnavi | 2023-07-07 | WIP
8 | Setup - Logic Function |  |  | Vedant | 2023-07-07 | WIP
9 | Setup - Event grid |  |  | Prashant | 2023-07-07 | WIP
10 | Test - Azure Function APP |  |  | Vedant | 2023-07-07 | Open
11 | Test - Web API |  |  | Roshan | 2023-07-07 | Open
12 | Test - Other Resources |  |  | Suyog | 2023-07-07 | Open
13 | Test - Storage Account |  |  | Vedant | 2023-07-07 | Open
14 | Test - Blob Storage |  |  | Suyog | 2023-07-07 | Open
15 | Test - Event grid |  |  | Prashant | 2023-07-07 | Open
16 | Test - Azure Logic App |  |  | Vaishnavi | 2023-07-07 | Open